## Slide 1: MONITORING & evaluation

## Slide 2
MONITORING
Is a regular systematic collection and analysis of information to track the progress of program implementation against pre-set targets and objectives. It aims to answer the question “did we deliver?”
Monitoring; Clarifies program objectives, Links activities and their resources to objectives, translates objectives into performance indicators and sets targets, Routinely collects data on these indicators, compares actual results with targets
Reports progress to team members and alerts them to problems

## Slide 3
Monitoring gives information on where a policy, program or project is at any given time relative to respective targets and outcomes
Monitoring focuses in particular on efficiency, and the use of resources

## Slide 4
While monitoring provides records of activities and results, and signals problems to be remedied along the way, it is descriptive and may not be able to explain why a particular problem has arisen, or why a particular outcome has occurred or failed to occur.
Evaluation deals with questions of cause and effect.
It is assessing or estimating the value, worth or impact of an intervention and is typically done on a periodic basis – perhaps annually or at the end of a phase of a project or program.

## Slide 5
EVALUATION
It is an objective assessment of an ongoing or recently completed project, program or policy, its design, implementation and results. It answers the question “What has happened as a result?”
Evaluation Analyzes why intended results were or were not achieved, assesses specific casual contributions of activities to results.

## Slide 6
Examines implementation process, Explores unintended results, Provides lessons, highlights significant accomplishments or program potential and offers recommendations for improvement
Evaluation looks at the relevance, effectiveness, efficiency and sustainability of an intervention.
It provides evidence of why targets and outcomes are or are not being achieved and addresses issues of causality.

## Slide 7
IMPORTANCE OF MONITORING & EVALUATION
Monitoring and evaluation (M&E) helps those involved with any type of projects to assess if progress desired is being achieved.
M&E can improve management. By monitoring progress against defined goals, a project team can assess what is working and what is not, and from there can determine what changes should be made to a project.

## Slide 8
M&E can be used to demonstrate progress to internal management and to external stakeholders.
Internally, measurable results can justify continued funding and clarify the return on investment of community development efforts to DCPCs and shareholders.
Externally, the results of M&E can demonstrate commitment to and competence in community development, and thus help a DCPC maintain its social license to operate.

## Slide 9
M&E is an opportunity to influence the design and execution of community development projects.
Furthermore, by providing feedback on whether programs are achieving aims in line with community needs and desires, M&E is a powerful accountability mechanism.

## Slide 10
Steps to follow when undertaking M&E
1. Be focused on what to Monitor & Evaluate - Checklist
2. Agreeing some guiding principles
It is useful to develop some guiding principles to ensure that your M&E is relevant, useful, timely and credible. Some examples might include making sure the M&E and/or information you collect is:
focused and feasible in relation to your available resources so that it supports rather than diverts resources from action

## Slide 11
i.e. make sure you focus information collection on what you ‘need to know’, not on what would be ‘nice to know’;
useful and timely information to improve group learning, group decision making, and project design;
useable by, and/or comparable to, data collected by other stakeholders so it contributes to the wider evidence base;
credible, valid and reliable to the extent possible within your available resources;

## Slide 12
sensitive to unequal power relations when you collect information (i.e. ensure that you listen to people who might be marginalized in the community or do not have a strong voice);
ethical e.g. in relation to data consent and protection

## Slide 13
3. Deciding which programmes/projects you need to monitor
It is important to decide and priotise the programmes or projects you will monitor as it is unlikely you will have the resources to monitor all your interventions at the same time. So, you will need to think about which programmes or projects you want to assess; over what time period; and whether it is an on-going activity which requires monitoring or a completed activity which requires evaluation.

## Slide 14
4. Deciding who to involve in the different stages of your M&E
To ensure M & E is relevant to your stakeholders it is important that you consider their information needs, as well as your own. You will therefore need to identify the key internal and external stakeholders, and decide how to involve them in the design, implementation, analysis and/or communication of findings;

## Slide 15
Examples of people you might want to include are (a) people directly involved in your projects (b) stakeholders in your wider community (geographic or community of interest) such as specific groups of residents, specific networks, community groups, the wider movement and/or (c) external stakeholders e.g. funders, local and national policy makers. It might also be possible to work in partnership with University departments.

## Slide 16
5. Deciding the key issues and questions you will want to investigate
The next key step is to identify the issues and questions you wish to learn about, and hence monitor.
These often include:
Issues and questions internal to your group
Organizational capacity/group processes – how well are you working together in relation to the following?
- needed resources (human, financial, technical)
- leadership and vision

## Slide 17
- management (e.g. clarity about aims, objectives, roles & responsibility; adaptability)
- cost effectiveness
sustainability (e.g. finance and/or volunteer burn out)
Joint working – how well are you working with others, for example
- in relation to partnerships, the wider movement, alliances, coalitions
- disseminating or sharing good practice and techniques

## Slide 18
Issues and questions external to your group
Relevance/acceptability - how relevant are your projects to different demographic sections of the community?
Effectiveness - are you achieving your objectives (e.g. in relation to attitudes & values; behaviours; public support; community capacity/local resilience; the wider movement; improved policies & increased democratic space)? What internal or external factors are facilitating/constraining progress?

## Slide 19
Impact - what is your impact on people’s lives (e.g. in relation to the ultimate changes in people’s lives or environment as a result of our initiatives)?
Contribution/attribution - what contribution have you made to outcomes and impacts (in relation to other factors/actors)?
You will need to decide whether or not to monitor or evaluate all of these questions or just some.
This is likely to require balancing information needs with available resources.

## Slide 20
6.Clarifying your aims, objectives, activities and pathways to change
In order to assess progress, you need to know what you are trying to achieve and how: that is, your aims, objectives and planned activities and then plan the activities that you and other actors) will carry out to achieve them.

## Slide 21
Doing M&E can help you assess what difference DCPCs are making and can provide vital intelligence, for example to help you:
assess and demonstrate your effectiveness in achieving your objectives and/or impacts on people’s lives;
improve internal learning and decision making about project design, how the group operates, and implementation i.e. about success factors, barriers, which approaches work/ don’t work etc.;

## Slide 22
empower and motivate volunteers and supporters;
ensure accountability to key stakeholders (e.g. your community, your members/supporters, the wider movement, funders, supporters);
influence government policy
share learning(best practices) with other communities and the wider movement;
contribute to the evidence base about effectiveness and limits of community action.

## Slide 23
Note that Monitoring and Evaluation are Complementary to each other

## Slide 24
I Thank you ALL for Your Attention!
Enjoy your Evening!